## Slide 1
Massachusetts All-Payer Claims Database: Technical Assistance Group (TAG)
July 11, 2017

## Slide 2: Agenda
APCD Version 6.0
Annual Premiums Data Request and Enrollment Trends Updates
Housekeeping Items
Wrap Up

## Slide 3: Intake APCD Version 6.0
MA APCD Intake Process | Intake 6.0 Timeline
Proposals Shared/Discussed with Carriers | December 2016/January 2017
New sftp testing | January 2017
Draft Submission Guides published | January 2017
Guides Reviewed at Technical Advisory Group | January 2017
Carrier Comment Period | January 2017
New sftp Pilot | April 2017
Administrative Bulletin and Guides Adopted | February 2017
Development/Testing | February/July 2017
Carrier Testing – new guides and new transmission process | July/August 2017
MA APCD Intake Version 6 Production | September 2017

## Slide 4: Intake APCD Version 6.0
July 2017 – continue testing for File Secure
August 2017 – edit testing for MA APCD Intake 6.0
September 2017 – both July 2017 and August 2017 production data due at CHIA (this means a one month delay on submission of July data)
All V6.0 files must be sent using File Secure

## Slide 5: Intake APCD Version 6.0
File Secure rolled out to all APCD submitters at the end of June
Contact our help desk with any issues (include screenshot of error if possible). Email: CHIA-DL-Data-Submitter-HelpDesk@MassMail.State.MA.US
CHIA compiling File Secure/SFTP FAQ to share with carriers

## Slide 6
CHIA Reporting Updates:
Annual Premiums Data Request
and Enrollment Trends
July 11, 2017
Ashley Storms | Analytic Reporting Manager
Lauren Almquist | Manager of Analytics

## Slide 7
Annual Premiums Data Request

## Slide 8
Thank you for participating in the 2017 Annual Premiums Data Request. Payer data is currently being incorporated into CHIA’s 2017 Annual Report on the Performance of the Massachusetts Health Care System.
Payers with merged market (individual and/or small group) plans: please add available 3R* transfer amounts for 2016 to your completed data submission workbooks and submit to Dianna Welch by July 17, 2017.
  2016 risk corridor payments need not be included at this time.
All data submitters: please respond to any outstanding data questions, including any requested resubmissions, by July 17, 2017.
Annual Premiums Data Request Update
*Risk adjustment, risk corridors, reinsurance

## Slide 9
Annual Premiums Data Request Timeline
May 2017 | Jun. 2017 | Jul. 2017 | Aug. 2017 | Sept. 2017
Initial submissions due |  |  |  | 
 |  | CHIA requests updated 3R amounts |  | 
 |  | 3R addendum submissions due |  | 
 |  |  | Reporting | 

## Slide 10
Enrollment Trends

## Slide 11: Enrollment Trends Update
Thank you to all who reviewed MA APCD data for the upcoming Enrollment Trends report. Your support is critical for the reporting of accurate and timely enrollment data.
The next Enrollment Trends report will be released in August 2017.

## Slide 12
Enrollment Trends Timeline
Apr. 2017 | May 2017 | Jun. 2017 | Jul. 2017 | Aug. 2017
Payers submit March 2017 MA APCD files |  |  |  | 
 | Supplemental enrollment reports due (select payers) |  |  | 
 |  | MA APCD enrollment counts sent to payers for review |  | 
 |  |  | Reporting | 

## Slide 13
Contact Information
For Annual Premiums technical questions and data submission:
Contact Dianna Welch at dianna.welch@oliverwyman.com
For Annual Premiums reporting and general questions:
Contact your CHIA liaison and Ashley Storms at ashley.storms@state.ma.us
For Enrollment Trends questions:
Contact your CHIA liaison and Lauren Almquist at lauren.almquist@state.ma.us

## Slide 14: Housekeeping Items
Member Month Tracker reports:
April 2017 last report requiring signoff (by 7/19)
May 2017 final report – no signoff required
DOI Reporting:
Q1 2017 Membership signoff due 7/14
Feedback on initial Utilization reports due 7/17
During upcoming bi-weekly calls, CHIA staff available to answer questions

## Slide 15: Next Meetings
August 8, 2017 @ 2:00 pm
September 12, 2017 @ 2:00 pm

## Slide 16
Questions?